## Summary
📊 Weekly Project Status Report
Generated: April 21, 2026
Tasks Completed |  | Budget Used | Overdue Tasks | Team Utilization
0/20 (0%) |  | $25,442 / $47,513 (54%) | 4 | 55%
Status Breakdown
Status | Count | % of Total
In Progress | 11 | 55.0%
Not Started | 5 | 25.0%
Overdue | 4 | 20.0%

## Tasks
Task ID | Task Name | Assigned To | Status | Due Date | Completion %
T-001 | Schedule Documentation meeting | Bob Martinez | In Progress | 2026-04-10 | 58%
T-002 | Validate Testing output | David Nguyen | Overdue | 2026-04-19 | 15%
T-003 | Migrate Research data | Bob Martinez | Overdue | 2026-04-07 | 23%
T-004 | Configure Testing pipeline | Alice Chen | Not Started | 2026-04-27 | 0%
T-005 | Set up Documentation environment | Bob Martinez | In Progress | 2026-04-22 | 67%
T-006 | Research Research options | Carol Kim | In Progress | 2026-04-26 | 51%
T-007 | Integrate Documentation service | Emma Wilson | In Progress | 2026-04-11 | 52%
T-008 | Update Testing module | Carol Kim | In Progress | 2026-04-27 | 60%
T-009 | Migrate Documentation data | Carol Kim | In Progress | 2026-04-11 | 33%
T-010 | Write Documentation tests | David Nguyen | In Progress | 2026-04-08 | 56%
T-011 | Set up Development environment | David Nguyen | Not Started | 2026-04-09 | 0%
T-012 | Fix Testing bug | David Nguyen | In Progress | 2026-04-27 | 61%
T-013 | Configure Testing pipeline | David Nguyen | Overdue | 2026-04-24 | 26%
T-014 | Optimize Design performance | Bob Martinez | Not Started | 2026-04-22 | 0%
T-015 | Write Design tests | Alice Chen | In Progress | 2026-04-26 | 32%
T-016 | Review Deployment requirements | Carol Kim | In Progress | 2026-04-24 | 65%
T-017 | Set up Research environment | Carol Kim | In Progress | 2026-04-21 | 36%
T-018 | Research Deployment options | Alice Chen | Not Started | 2026-04-12 | 0%
T-019 | Write Research tests | Bob Martinez | Overdue | 2026-04-19 | 46%
T-020 | Validate Research output | David Nguyen | Not Started | 2026-04-22 | 0%

## Budget
Category | Allocated ($) | Spent ($) | Remaining ($)
Design | 8306 | 3343.38 | 4962.62
Development | 4931 | 3655.09 | 1275.91
Testing | 7214 | 6079.77 | 1134.23
Infrastructure | 13869 | 6817.22 | 7051.78
Marketing | 5253 | 2209.5 | 3043.5
Operations | 7940 | 3337.53 | 4602.47

## Team
Member | Total Tasks | Completed | In Progress | Overdue
Alice Chen | 3 | 0 | 1 | 0
Bob Martinez | 5 | 0 | 2 | 2
Carol Kim | 5 | 0 | 5 | 0
David Nguyen | 6 | 0 | 2 | 2
Emma Wilson | 1 | 0 | 1 | 0